## Schedule
Java Air Project Schedule | [35 empty] | Author: Steve Jia
[6 empty] | Period Highlight: |  |  |  |  | 20 |  |  |  | Plan |  |  | Actual |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan) | Creation: 9/10/2016
Last Updated: 11/4/2016
Version 1.2 | [16 empty] | Fall
[6 empty] | PERIOD | [10 empty] | Break | [11 empty] | Thanksgiving
[6 empty] | ENDS |  | WK3 |  | WK4 |  | WK5 |  | WK6 |  | WK7 |  | WK8 |  | WK9 |  | WK10 |  | WK11 |  | WK12 |  | WK13 |  | WK14 |  | WK15 |  | WK16
| PLAN | PLAN | ACTUAL | ACTUAL | PERCENT | 2016-09-03 | 2016-09-07 | 2016-09-10 | 2016-09-14 | 2016-09-17 | 2016-09-21 | 2016-09-24 | 2016-09-28 | 2016-10-01 | 2016-10-05 | 2016-10-08 | 2016-10-12 | 2016-10-15 | 2016-10-19 | 2016-10-22 | 2016-10-26 | 2016-10-29 | 2016-11-02 | 2016-11-05 | 2016-11-09 | 2016-11-12 | 2016-11-16 | 2016-11-19 | 2016-11-23 | 2016-11-26 | 2016-11-30 | 2016-12-03 | 2016-12-07 | 2016-12-10
ACTIVITY | START | DURATION | START | DURATION | COMPLETE | 2016-09-03: PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
MILESTONES
Project Initiation / Team Formed | bar: PERIODS 1
Core Requirements/Features Established | bar: PERIODS 5
Initial Design Created | bar: PERIODS 9
Prototype Demo | bar: PERIODS 16
Freeze Requirements | bar: PERIODS 17
Class Designs Finalized | bar: PERIODS 18
Implementation Completed | bar: PERIODS 21
Testing Completed | bar: PERIODS 23
Project Completion | bar: PERIODS 27
PM (Steve)
Develop Detailed Schedule | 3 | 2 | 3 | 2 | 100%
Revise / Update Schedule | 5 | 8 | 4 | 17 | 90%
Develop SPMP Document | 4 | 9 | 4 | 16 | 100%
Announce Task Assignments of Unit Impl. | 13 | 1 | 17 | 1 | 100%
Functioning Point Analysis | 14 | 2 | 17 | 1 | 100%
Revise Task Assignment | 15 | 2 | --- | --- | 0%
RE (Yuwei, Guoyu)
Develop Initial SRS Document | 2 | 4 | 2 | 7 | 100%
Review SRS Document With Team | 6 | 1 | 7 | 11 | 100%
Revise SRS Document Based On Changes | 6 | 6 | 7 | 11 | 100%
SA (Rui)
Review SRS Document with RE | 5 | 4 | 7 | 2 | 100%
Translate SRS Into Technical Specification | 5 | 4 | 7 | 4 | 100%
Develop Initial UML Design Document | 7 | 6 | 7 | 4 | 100%
Preliminary Design Review | 12 | 1 | 16 | 1 | 100%
Develop Detailed UML Design Document | 12 | 4 | 11 | 10 | 70%
Develop Help Documents | 22 | 7 | --- | --- | 0%
IE (Amy)
Develop GUI and Menu Standards Document | 5 | 7 | 9 | 9 | 100%
Develop Configuration Management Plan | 5 | 9 | 9 | 9 | 100%
Review and Revise GUI Interfaces with Team | 14 | 3 | 14 | 7 | 95%
Demo Prototype with Dr. Zhang | 16 | 1 | 16 | 1 | 100%
Demo Integrated Product (Any Time) | 23 | 6 | --- | --- | 0%
TE (Matt, Xu)
Develop Database ER Diagram | 3 | 10 | 3 | 10 | 100%
Develop Quality Assurance Plan Document | 5 | 15 | 8 | 14 | 75%
Develop Verification and Validation Document | 5 | 20 | 8 | 14 | 60%
Develop Software Test Document | 5 | 23 | 15 | 8 | 60%
Testing, Testing, and More Testing | 21 | 7 | --- | --- | 0%
CD (All)
Create Database Tables | 9 | 5 | 18 | 4 | 50%
Develop Database Queries | 9 | 5 | 18 | 4 | 80%
Develop Java Swing Forms | 9 | 8 | 14 | 8 | 80%
Develop Source Code for "Customer" Class | 13 | 10 | 14 | 4 | 100%
Develop Source Code for "Passenger" Class | 13 | 10 | 17 | 5 | 100%
Develop Source Code for "Flights" Class | 13 | 10 | 17 | 5 | 100%
Develop Source Code for "Data Client" Class | 13 | 10 | 17 | 5 | 50%
Develop Source Code for Other Classes | 13 | 10 | 17 | 5 | 50%
Bug Fixes and Program Improvement | 23 | 5 | --- | --- | 0%

## Change History
Date | Version | Author | Change Description
2016-09-12 | 0.1 | S. Jia | Initial Creation
2016-10-03 | 0.2 | S. Jia | Added Milestones